## Q2-2021
Week | FLASK ML Application | Estimated Effort in Hours | Actual Effort in Hours | Task Desciption
2021-04-15 | Requirements gathering | 5 | 4 | Creation Epics/Features/user stories
2021-04-22 | Planning for Implementation | 10 | 12 | Scheduling meetings and conduction meeting with all stake holders of project
2021-04-29 | Setting up Azure Cloud Shell for CI | 2 | 1 | Preparation of Azure cloud shell, with SSH key, installing required packages
2021-05-06 | Setting up Azure Web App on Azure Cloud Platform | 4 | 4 | Setting up azure resource group, azure AppService and deploying azure web application
2021-05-13 | Configuring GitHub Actions | 5 | 3 | Configuring the GitHub workflow yaml
2021-05-20 | Implementation test cases for testing | 5 | 4 | Creation of makefile with python virtual environment, installing dependent packages, testing and linting packages etc
2021-05-27 | Setup of Azure DevOps Project for Flask ML Application | 8 | 10 | Creation Azure DevOps project
2021-06-03 | Setup of Azure pipeline setup for Continuous Delivery | 3 | 2 | Creation of azure pipeline setup for deploying the flask ml source code
2021-06-10 | Creation of Deployment Documentation | 8 | 10 | Documenting all the steps for deploying the flask ml application using azure pipeline
2021-06-17 | Project Demo | 2 | 2 | Demo to customer
2021-06-24 | Deploy to Production | 1 | 1 | Load and smoke test and deploy to production
2021-07-01 | Enhancements and Maintenance | 5 | 5 | hotfixes and gathering new features
| Goals | Goals
Project Epics/Features Preparation
Planning for Project Implementation
Planning for Infrastructure Setup
Planning for Application features
Preparation of MVP Demo
Preparation of Release plan
Deployment to Production